## Sheet1
Yuba College Objectives
Educational Master Plan 2017-2020
Objective 1 |  | DISTRICT GOAL 1: Increase student success and maximize the student experience through learner centered programs and services designed to enhance student learning and completion.
OBJECTIVE 1.1– Connection * 2017-2018: By June 30, 2018, increase the number of new student enrollments by 2%. * 2018-2019: By June 30, 2019, increase the number of new student enrollments by 2%. * 2019-2020: By June 30, 2020 increase the number of new student enrollments by 2%.
|  | ACTIONS | PERFORMANCE OUTCOMES | TIMELINE | FUNDING SOURCE | RESPONSIBLE PARTY
2017-2018 Objective: By June 30, 2018 increase the number of new student enrollments by 2%.
|  | Develop and implement a plan to increase FAFSA and Dream Act application. Plan will include strategies such as increased marketing activities, direct communication with students, on-campus workshops, and classroom presentations. | Plan, Completion Data | 2017-2020 | GF | Director of Financial Aid
|  | Develop and implement a plan to increase the number of first-time students receiving an AEP prior to registration. Plan will include strategies and implementation timelines for activities such as the development of an online module, targeted marketing, and improved data colletion and reporting for AEP exemptions. | Plan, Number of AEPs | 2017-2020 | SSSP | Director of Counseling
|  | Develop and implement a comprehensive and integrated outreach and marketing plan aligning high school outreach activities, parent targeted outreach, CTE activities, peer ambassador in reach and outreach, etc. to increase student enrollments. | Plan, Application data | 2017-2019 | GF | Dean of Student Success, College Marketing and Promotion Coordinator, & Outreach Committee
2018-2019 Objective: By June 30, 2019 increase the number of new student enrollments by 2%.
|  | Develop promotional materials and a marketing program to increase the awareness of the benefits of the Associate Degrees for Transfer. | Application and degree data | 2018-2019 | GF, AEBG, SWF, EQUITY | College Marketing and Promotion Coordiator and Director of Counseling
|  | Evaluate the Quick Reg Program and modify the program as appropriate to improve outcomes. | Student registration | 2018-2019 | EQUITY | VP and Director of Counseling
2019-2020 Objective: By June 30, 2020 increase the number of new student enrollments by 2%.
|  | Evaluate the Peer Center/Welcome Center services and scale as appropriate. | Student registration | 2019-2020 | GF, SSSP | Dean of Student Services
OBJECTIVE 1.2– Entry * 2017-2018: By June 30, 2018, increase the rate of students completing transfer-level math and English coursework in two years by 2% (IEPI Goal). * 2018-2019: By June 30, 2019, increase the rate of students completing transfer-level math and English coursework in two years by 3% (IEPI Goal). * 2019-2020: By June 30, 2020, increase the rate of students completing transfer-level math and English coursework in two years by 3% (IEPI Goal).
|  | ACTIONS | PERFORMANCE OUTCOMES | TIMELINE | FUNDING SOURCE | RESPONSIBLE PARTY
2017-2018 Objective: By June 30, 2018 increase the rate of student completing transfer-level math and English coursework in two years by 2%.
|  | Send a team of faculty, staff, and administrators to the California Guided Pathways Institutes. | Training, identification of best practices, data analysis, & pilot implemention | 2017-2019 | IEPI, GF | Dean of Applied Academics
|  | Create a task force of faculty, staff and administrators to establish clear student success goals and identify coordinated and scalable strategies to improve student outcomes. Engage the college community in collaborative discussions around how to improve student success in areas such as number of college credits earned in first term and first year, completion of math and English in student's first year, persistence from term to terms and rates of college-level course completion. Create a sense of urgency for change. | Goals, data, recommendations, plan, & plan | 2017-2020 | EQUITY, GF, SSSP | President, Vice President, Academic Senate & Guided Pathways Task Force
|  | Implement multiple measures. | Improved placement evidenced by success and retention data | 2017-2019 | SSSP | Dean of Student Services, Testing and Assessment Coordinator, SAI Workgroup
|  | Develop a dual enrollment program with all local high school districts. Initiate a pilot program during the fall 2018 semester. | MOUs, enrollment data, success and retention data | 2017-2019 | EQUITY | Dean of Student Success, College Marketing and Promotion Coordinator, & Outreach Committee
|  | Evaluate the effectiveness of embedded ESL tutoring and Embedded Peer Mentors for Accelerated English. Expand the program and continue data evaluation and analysis. | Success and retention data | 2017-2018 | EQUITY, GF | Dean of STEM, Director of Academic Excellence, & Student Equity Committee
2018-2019 Objective: By June 30, 2019 increase the rate of student completing transfer-level math and English coursework in two years by 3%.
|  | Evaluate best practices and design and implement a First Year Experience (FYE) program. | Program development, success and retention data | 2019-2020 | EQUITY | Director of Counseling
2019-2020 Objective: By June 30, 2020 increase the rate of student completing transfer-level math and English coursework in two years by 3%.
|  | Review best practices, design and execute a summer bridge program. | Program development, success and retention data | 2019-2020 | EQUITY, GF | Dean of Student Services & Dean of Student Success
OBJECTIVE 1.3– Progress * 2017-2018: By June 30, 2018, increase the rate of students persisting from term to term by 3%. (Scorecard) * 2018-2019: By June 30, 2019, increase the rate of students persisting from term to term by 3%. (Scorecard) * 2019-2020: By June 30, 2020, increase the rate of students persisting from term to term 3%. (Scorecard)
2017-2018 Objective: By June 30, 2018 increase the rate of students persisting from year 1 to year 2 by 3%.
|  | Transition early alert to Student Services. Expand the utilization of Early Alert by increasing faculty awareness through Flex workshops, trainings, division presentations,student testimonials, etc. | Utilization rate | 2017-2018 | EQUITY, SSSP | Dean of Student Services
|  | Implement curriculum and degree rotational update system. | Currency of curriculum | 2017-2018 | GF | Curriculum Committee
|  | Update all out of date degrees and certificates. | Currency of degrees & certificates | 2017-2019 | GF | Curriculum Committee
|  | Implement new catalog development process and interactive, searchable online catalog. Organize College catalog around programs tied to transfer and career pathways. | Online catalog | 2017-2019 | GF | Vice President & College Marketing and Promotion Coordinator
2018-2019 Objective: By June 30, 2019 increase the rate of students persisting from year 1 to year 2 by 3%.
|  | Expand the Student Ambassador Club to support peer engagement. | Student enrollment and achievement data | 2018-2019 | EQUITY | Program Coordinator
|  | Implement Degree Audit | Electronic Ed Plans | 2018-2019 | SSSP | Dean of Student Services
| * | Develop five additional AS-T/AA-T degrees. | Degrees | 2018-2019 | GF | Curriculum Committee
|  | Increase student participation in the Puente, Umoja and MESA programs. | Student enrollment and achievement data | 2018-2019 | EQUITY | Program Coordinator, Equity & SSSP Committees
2019-2020 Objective: By June 30, 2020 increase the rate of students persisting from year 1 to year 2 by 3%.
|  | Increase participation in Student Success Symposiums | Success and retention data | 2019-2020 | EQUITY, SSSP | Director of Academic Excellence & Director of Counseling
OBJECTIVE 1.4– Completion * 2017-2018: By June 30, 2018, increase the rate of students completing certificates, degrees, and are transfer ready by 5%. (IEPI Goal-Overall #12) * 2018-2019: By June 30, 2019, increase the rate of students completing certificates, degrees, and are transfer ready by 5%. (IEPI Goal-Overall #12) * 2019-2020: By June 30, 2020 increase the rate of students completing certificates, degrees and are transfer ready by 5%. (IEPI Goal-Overall #12)
2017-2018 Objective: By June 30, 2018 increase the rate of students completing certificates, degrees, and are transfer ready by 5%.
|  | Research if students can be automatically awarded degrees and certificates without utilizing the existing petition process and without a negative impact on financial aid options. | Research and recommendation | 2017-2018 | SSSP | Dean of Student Services
|  | Analyze Transfer Center operations, programs and activities. Research statewide best practices and create Transfer Center Program Plan. | Plan | 2017-2018 | SSSP, EQUITY | Dean of Student Services, Director of Counseling, & Transfer Counselor
2018-2019 Objective: By June 30, 2019 increase the rate of students completing certificates, degrees, and are transfer ready by 5%.
|  | Initiate faculty to faculty and executive level conversations with key transfer institutions to identify ways to improve transfer outcomes. | Transfer rates | 2018-2019 | GF | President, Vice President, & Academic Senate
|  | Admission and Records will perform degree audits to identify students who have completed degree requirements, but not yet applied for a degree. Students who have departed, but are near completion will also be contacted. Automate degree audit process. | Degrees and certificates | 2017-2018 | SSSP | Dean of Student Services
2019-2020 Objective: By June 30, 2020 increase the rate of students completing certificates, degrees, and are transfer ready by 5%.
|  | Develop a comprehensive internship and job placement program. | Internship and job placement rates. | 2017-2020 | SWP | Dean of Applied Academics and CWEE Coordinator
DISTRICT GOAL 2: Integrate planning and institutional effectiveness processes with a culture of evidence.
OBJECTIVE 2.1– Finalize implementation of resource allocation model.
|  | ACTIONS | PERFORMANCE OUTCOMES | TIMELINE | FUNDING SOURCE | RESPONSIBLE PARTY
|  | Assess effectiveness of one-time allocation process changes and scale for on-going allocations. | Evaluation and Implementation | 2017-2019 | GF | Planning & Budget Committee
|  | Implement CEAC rubric for one-time allocations. | Implementation | 2017-2018 | GF | Planning & Budget Committee
|  | Incorporate facilities into resource allocation model process. | Implementation | 2017-2018 | GF | Planning & Budget Committee
|  | Incorporate staffing into resource allocation model process. | Implementation | 2018-2019 | GF | Planning & Budget Committee
|  | Develop a process to ensure that categorical funding (BSI, SSSP, SEP, SWP, etc.) aligns with the Educational Master Plan and informs the resource allocation process. | Implementation | 2018-2019 | GF | Planning & Budget Committee
OBJECTIVE 2.2: Integrate authentic SLO/SAO assessment data into the planning processes.
|  | Improve assessment practices. | Process development | 2017-2018 | GF | SLO Committee & Academic Senate
OBJECTIVE 2.3: Build capacity for data infrastructure.
|  | Coordinate Planning Office and YC and District Technology Committees to identify infrastructure needs. | Plan | 2017-2018 | GF | Technology Committee
|  | Complete development of dashboards. | Tool | 2018-2020 | GF | Technology Committee
|  | Coordinate campus-wide training on use of data. | Training | 2018-2020 | GF | Technology Committee
DISTRICT GOAL 3: Strengthen our CORE as a 21st-century, learning-centered organization; employ, develop and sustain highly professional, qualified faculty and staff.
OBJECTIVE 3.1-By 2020, improve communication and collaboration across the campus and centers as measured by campus survey data.
|  | Identify a task force charged with creating an actionable plan to address the areas of concern identified in the Gruffalo Noel-Levitz College Employees Satisfaction Survey (CESS), the Survey of Entering Student Engagement (SENSE), and the Community College Survey of Student Engagement. The plan should address how to improve spirit of teamwork and cooperation, communication, and orientation and ongoing training. | Plan | 2017-2018 | GF | College Council
DISTRICT GOAL 4: Complete multi-college district transition in structure, rules, responsibilities, and processes.
None
DISTRICT GOAL 5: Assert regional educational, economic and workforce leadership; prioritize Economic and Workforce Development Programs based on regional, state and national imperatives.
OBJECTIVE 5.1- By 2020, collaborate with local industry, government organizations, and other educational institutions to explore non-credit pathways aligned with YC credit programs.
|  | ACTIONS | PERFORMANCE OUTCOMES | TIMELINE | FUNDING SOURCE | RESPONSIBLE PARTY
|  | Create a task force to analyze noncredit offerings and identify areas of possible expansion. Identify pathways to credit offerings evaluating expanded CTE, ESL, contract education, and community education offerings. | Plan | 2017-2018 | AEBG, SWF | Dean of Arts and Education and Dean of Applied Academics.
|  | Examine contract education opportunities focused on serving active duty military members via online class offerings. | Plan | 2017-2018 | GF | Director, Campus Operations